## PSP1.1 Project Plan Summary
PSP1.1 Project Plan Summary
Student | Juan Camilo Mendieta Silva |  | Date | 2013-02-17
Program | Programa 4 – Calculo Rangos de Tamaño LOC usando Desviación Estándar |  | Program # | 4
Instructor | Luis Daniel Benavides |  | Language | JAVA
| Plan | Actual | To Date
Summary
Size/Hour | 56.1538 | 74.2188 | 130.3688
Planned Time | 7.5 |  | 11
Actual Time |  | 9.86 | 1625.86
CPI (Cost-Performance Index) |  |  | 0.76065
(Planned/Actual)
% Reused | 64.6259 | 46.6667 | 46.6667
% New Reusable | 5.1932 | 3.9394 | 3.9394
| Plan | Actual | To Date
Program Size
Base (B) | 0 | 0
| (Measured) | (Measured)
Deleted (D) | 0 | 0
| (Estimated) | (Counted)
Modified (M) | 0 | 0
| (Estimated) | (Counted)
Added (A) | 143.86 | 190
| (A+M - M) | (T - B + D - R)
Reused (R) | 140 | 140 | 303
| (Estimated) | (Counted)
Added and Modified (A+M) | 143.86 | 190 | 920
| (Estimated) | (A + M)
Total Size (T) | 216.6313 | 330 | 1223
| (Projected) | (Measured)
Total New Reusable | 11.25 | 13 | 87
Estimated Proxy Size (E) | 143.86
| Plan | Actual | To Date |  | To Date %
Time in Phase (horas.)
Planning | 1 | 3.5 | 12.06 |  | 26.1492
Design | 1 | 2.5 | 7.06 |  | 15.3079
Code | 3 | 2.56 | 17.1 |  | 37.0772
Compile | 0.5 | 0.5 | 2.5 |  | 5.4206
Test | 1 | 0.8 | 4.4 |  | 9.5403
Postmortem | 1 |  | 3 |  | 6.5048
Total | 7.5 | 9.86 | 46.12 |  | 100
|  | Actual | To Date |  | To Date %
Defects Injected
Planning |  | 0 | 0 |  | 0
Design |  | 2 | 8 |  | 42.1053
Code |  | 2 | 7 |  | 36.8421
Compile |  | 0 | 0 |  | 0
Test |  | 0 | 4 |  | 21.0526
Total Development |  | 4 | 19
Defects Removed
Planning |  | 0 | 0 |  | 0
Design |  | 0 | 0 |  | 0
Code |  | 2 | 25 |  | 69.4444
Compile |  | 0 | 0 |  | 0
Test |  | 2 | 7 |  | 19.4444
Total Development |  | 4 | 36 |  | 100
After Development |  | 0 | 0

## Size Estimating Template (hidden)
Size Estimating Template
Student | Juan Camilo Mendieta Silva |  |  |  |  | Date |  | 2013-02-17
Program | Programa 4 – Calculo Rangos de Tamaño LOC usando Desviación Estándar |  |  |  |  | Program # |  | 4
Instructor | Luis Daniel Benavides |  |  |  |  | Language |  | JAVA
Estimated
Base Parts |  | Base |  | Deleted |  | Modified |  | Added
|  | 0 |  | 0 |  | 0 |  | 0
Total | B | 0 | D | 0 | M | 0 | BA | 0
Actual
Base Parts |  | Base |  | Deleted |  | Modified |  | Added
|  | 0 |  | 0 |  | 0 |  | 0
Total |  | 0 |  | 0 |  | 0 |  | 0
|  | Estimated | [6 empty] | Actual
Parts Additions |  | Type |  | Items |  | Rel. Size |  | Size* | Size* | Items
RangoTamanoRelativo |  | Data |  | 4 |  | S |  | 19.16 | 23 | 5
CalculoTamanoRelativo |  | Calc |  | 1 |  | M |  | 11.25 | 15 | 1
PanelCalculoTamanoRelativo |  | I/O |  | 2 |  | M |  | 32.3 | 51 | 2
InterfazCalculoRangoTamaoRelativoDE (Principal) |  | I/O |  | 3 |  | L |  | 64.86 | 63 | 2
CalculoTamanoRelativoTest |  | Set-Up |  | 1 |  | S |  | 5.04 | 24 | 1
Calculo (Se marca con *, para determinar que es reutilizable) |  | Calc |  | 2 |  | M |  | 11.25 | 13 | 2
Total | [6 empty] | PA | 143.86 | 189 | 13
|  | Estimated |  | Actual
Reused Parts |  | Size |  | Size
Calculo |  | 43 |  | 57
Lista |  | 51 |  | 51
Nodo |  | 25 |  | 25
PanelEncabezado |  | 21 |  | 21
Total | R | 140 |  | 154
PROBE Calculation Worksheet (Added and Modified) |  | Size |  | Time
Added size (A): A = BA+PA |  | 143.86
Estimated Proxy Size (E): E = BA+PA+M |  | 143.86
PROBE estimating basis used: (A, B, C, or D) |  | C |  | C
Correlation: (R2) |  | N/A |  | N/A
Regression Parameters: b0 Size and Time |  | 0 |  | 0
Regression Parameters: b1 Size and Time |  | 0.53268 |  | 1.9238
Projected Added and Modified Size (P): P = b0size + b1size*E |  | 76.6313
Estimated Total Size (T): T = P + B - D - M + R |  | 216.6313
Estimated Total New Reusable (NR): sum of * items |  | 11.25
Estimated Total Development Time: Time = b0time + b1time*E |  |  |  | 276.7592
Prediction Range: Range |  | - |  | 274.142
Upper Prediction Interval: UPI = P + Range |  | - |  | 550.9012
Lower Prediction Interval: LPI = P - Range |  | - |  | 2.6173
Prediction Interval Percent: |  | - |  | 90
NOTA:
Se utiliza la siguiente tabla, propuesta en el libro de PSP
C++ Object Size in LOC per Method
Category | VS | S | M | L | VL
Calc | 2.34 | 5.13 | 11.25 | 24.66 | 54.04
Data | 2.6 | 4.79 | 8.84 | 16.31 | 30.09
I/O | 9.01 | 12.06 | 16.15 | 21.62 | 28.93
Logic | 7.55 | 10.98 | 15.98 | 23.25 | 33.83
Set-up | 3.88 | 5.04 | 6.56 | 8.53 | 11.09
Text | 3.75 | 8 | 17.07 | 36.41 | 77.66

## PSP Time Recording Log (hidden)
PSP Time Recording Log
Student | Juan Camilo Mendieta Silva |  |  |  | Date | 2013-02-15
Program | Programa 4 – Calculo Rangos de Tamaño LOC usando Desviación Estándar |  |  |  | Program # | 4
Instructor | Luis Daniel Benavides |  |  |  | Language | JAVA
Project | Phase | Start Date and Time | Int. Time | Stop Date and Time | Delta Time | Comments
Programa 4 | Planning - Requerimientos | 2013-02-16 21:00 | 0 h | 2013-02-16 21:30 | 0,5 h | Se realiza la especificación de requerimientos
Programa 4 | Planning - Diseño Conceptual | 2013-02-16 21:30 | 0h | 2013-02-16 22:30 | 1h | Se realiza el diseño conceptual para la estimaciòn de tamaños para cada una de las partes y items
Programa 4 | Planning - Plan Summary Form - Size Estimate | 2013-02-16 23:00 | 0h | 2013-02-17 01:00 | 2h | Se completa el Plan Summary y la plantilla de estimaciòn de tamaños de acuerdo al metodo PROB
Programa 4 | Desarrollo - Diseño | 2013-02-17 08:00 | 0h | 2013-02-17 10:30 | 2,5h | Elaboraciòn diseño de clases de las entidades establecidas.
Programa 4 | Desarrollo - Codificacion | 2013-02-17 20:13 | 0h | 2013-02-17 22:42 | 2,56h | Se realiza la codificaciòn del proyectos
Programa 4 | Desarrollo - Pruebas | 2013-02-17 20:13 | 0h | 2013-02-17 22:42 | 0,8h | Se realiza las pruebas de cada uno de los casos propuestos en el enunciado del requerimiento, completando el formato de pruebas de usuario.

## Probe - Size
Metodo C - Probe
|  | Programa 1 | Programa 2 | Programa 3 | Programa 4 | Total
Size Estimating Procedure 4C
(a+m) | actual total added and modified size to date | 0 | 253 | 321 | 241 | 815
| plan total added and modified size to date | 0 | 298 | 634 | 598 | 1530
| B0 | 0
| B1 = (actual total added and modified size to date/plan total added and modified size to date) | 0.53268 |  |  |  |  | 145.75 | 102.025 | 43.725 | 189.475

## Hoja1
PROBE Calculation Worksheet (Added and Modified) | Size | Time
Added size (A): A = BA+PA | 275
Estimated Proxy Size (E): E = BA+PA+M | 275
PROBE estimating basis used: (A, B, C, or D) | C | C
Correlation: (R2) | NA | NA
Regression Parameters: b0 Size and Time | 0 | 0
Regression Parameters: b1 Size and Time | 0.53268 | 1.9238
Projected Added and Modified Size (P): P = b0size + b1size*E | 146.4869 |  | 145.75 | 102.025
Estimated Total Size (T): T = P + B - D - M + R | 146.4869
Estimated Total New Reusable (NR): sum of * items | 10
Estimated Total Development Time: Time = b0time + b1time*E |  | 528
Prediction Range: Range | 102.5408 | 369.6 |  | 0.058824 | 5.8824
Upper Prediction Interval: UPI = P + Range | 249.0278 | 897.6
Lower Prediction Interval: LPI = P - Range | 43.9461 | 158.4
Prediction Interval Percent: | 70% | 70%

## Hoja2
5.016% | 6.0192 | 120 | 6 | 6
5.351% | 6.4213 | 120 | 6.4 | 6.4
62.87% | 75.444 | 120 | 12 | 12
14.21% | 17.052 | 120 | 51.4 | 51.4
12.54% | 15.0502 | 120 | 12 | 12
| 119.9867 |  | 0 | 0
|  |  | 17.1 | 17.1
|  |  | 15.1 | 15.1
|  |  | 81.4 | 120

## Probe - Time
Metodo C - Probe
|  | Programa 1 | Programa 2 | Programa 3 | Programa 4 | Total
Time Estimating Procedure 5C
| actual total development time to date | 0 | 384 | 634 | 598 | 1616 | 245.5
| estimated – total added and modified size to date | 0 | 420 | 300 | 120 | 840
| B0 | 0
| B1 = (actual total development time to date/estimated – total added and modified size to date) | 1.9238

## LOC_X_HORA - Rango (hidden)
Actual | Programa 2 | Programa 3 | Programa 4 | Total Ponderado
LOC Adicionadas y Modificadas | 339 | 391 | 190 | 730
Nhoras | 8 | 5 | 2.56 | 13
LOC x hora | 42.375 | 78.2 | 74.2188 | 56.1538
Rango | Tiempo (horas) | Tiempo Promedio
Mínimo | 3.3949 | 2.6173 |  | 2.6173
Maximo | 1.8396
Tamaño Estimado | 143.86